## DASHBOARD
Total Test Cases | 43 | Risk_Severity
Completed Test Cases | 39 | Critical | 24
Success Rate | 0.90698 | High | 26
Critical Defects | 24 | Medium | 79
|  | Low | 1
|  | Total | 130

## TEST_CASES
Test ID | Module | Test Case | Preconditions | Test Steps | Expected Result | Priority | Status | Defect ID
AUTH-001 | Authentication | Valid user registration | No user logged in | 1. Navigate to Register page | User account created, success message shown, redirected to login | High | Done | DEF-A001
2. Fill: Name, Email, Password, Confirm Password
3. Click Create Account
AUTH-002 | Authentication | Email validation | No user logged in | 1. Navigate to Register | Error message shown, form not submitted | High | Done | DEF-A002
2. Enter "invalid-email"
3. Submit form
AUTH-003 | Authentication | Password confirmation | No user logged in | 1. Navigate to Register | Error message for password mismatch | High | Done | DEF-A003
2. Enter different passwords
3. Submit form
AUTH-004 | Authentication | Successful login | Valid user exists | 1. Navigate to Login | Login successful, navigation updated, user info shown | High | Done | DEF-A004
2. Enter user@cleancity.com/password123
3. Submit
AUTH-005 | Authentication | Invalid credentials | No user logged in | 1. Navigate to Login | Error message shown, remains on login page | High | Done | DEF-A005
2. Enter wrong@email.com/wrongpass
3. Submit
AUTH-006 | Authentication | Admin login | Admin account exists | 1. Navigate to Login | Login successful, Admin link visible in navigation | High | Done | DEF-A006
2. Enter admin@cleancity.com/admin123
3. Submit
AUTH-007 | Authentication | User logout | User logged in | 1. Click logout button | Session cleared, redirected to login, nav updated | Medium | Done | DEF-A007
AUTH-008 | Authentication | Session persistence | User logged in | 1. Login successfully | User remains logged in, data persists | Medium | Done | DEF-A008
2. Refresh browser
3. Check state
AUTH-009 | Authentication | Role-based access | Regular user logged in | 1. Login as regular user | Admin link hidden from regular users | High | Done | DEF-A009
2. Check navigation menu
AUTH-010 | Authentication | Duplicate email registration | User already exists | 1. Try to register with existing email | Error message for duplicate email | High | Done | DEF-A010
2. Submit form
AUTH-011 | Authentication | Forgot password option | User logged in | 1. Login in with your credentials. | An option to change your password | High | Completed | DEF-A011
2. Put incorrect password
WM-001 | Waste Management | Submit valid pickup request | User logged in | 1. Navigate to Home | Success message shown, request stored | High | Done | DEF-W001
2. Fill: Name, Location, Waste Type
3. Submit
WM-002 | Waste Management | Required field validation | User logged in | 1. Navigate to Home | Validation error for name field | High | Done | DEF-W002
2. Leave name blank
3. Submit
WM-003 | Waste Management | Location selection required | User logged in | 1. Navigate to Home | Validation error for location | High | Done | DEF-W003
2. Don't select location
3. Submit
WM-004 | Waste Management | Waste type selection required | User logged in | 1. Navigate to Home | Validation error for waste type | High | Done | DEF-W004
2. Don't select waste type
3. Submit
WM-005 | Waste Management | Optional date field | User logged in | 1. Navigate to Home | Form submits successfully | Medium | Done | DEF-W005
2. Fill required fields only (no date)
3. Submit
WM-006 | Waste Management | Pick-up Scheduling | User logged in | 1. Navigate to Home page. | An error that it is a past date | High | Completed | DEF-W006
2. Fill the required fields.
3. On the preffered pickup date, try put a past date.
WM-007 | Dashboard | View all requests | User logged in, requests exist | 1. Navigate to Dashboard | All requests displayed with correct data | Medium | Done | DEF-W006
2. Check table
WM-008 | Dashboard | Filter by status | Multiple requests exist | 1. Go to Dashboard | Only pending requests displayed | Medium | Done | DEF-W007
2. Select "Pending" status filter
3. Check table
WM-009 | Dashboard | Filter by location | Multiple requests exist | 1. Go to Dashboard | Only Nairobi requests displayed | Medium | Done | DEF-W008
2. Select "Nairobi" location filter
3. Check table
WM-010 | Dashboard | Filter count display | Multiple requests exist | 1. Apply filters | Count updates with filtered results | Low | Done | DEF-W009
2. Check filter count text
WM-011 | Dashboard | Data persistence | Multiple requests submitted | 1. Submit requests | All requests persist after refresh | High | Done | DEF-W010
2. Reload page
3. Check dashboard
WM-012 | Dashboard | Profile Edit | User logged in | 1. Log in to the clean city app | Be able to change details of the profile i.e change email address | Medium | Completed | DEF-W011
2. Hover to the profile tab.
FB-001 | Feedback | Submit valid feedback | User logged in | 1. Navigate to Feedback | Success message shown | Medium | Done | DEF-F001
2. Fill Request ID and Reason
3. Submit
FB-002 | Feedback | Request ID validation | User logged in | 1. Navigate to Feedback | Validation error shown | Medium | Done | DEF-F002
2. Leave Request ID blank
3. Submit
FB-003 | Feedback | Reason selection required | User logged in | 1. Navigate to Feedback | Validation error shown | Medium | Done | DEF-F003
2. Don't select reason
3. Submit
ADMIN-001 | Admin | Admin access control | Regular user logged in | 1. Try to access admin page | Access denied or redirected | High | Done | DEF-AD001
2. Check access
ADMIN-002 | Admin | Admin features visibility | Admin user logged in | 1. Login as admin | All admin features visible and functional | High | Done | DEF-AD002
2. Navigate to Admin page
ADMIN-003 | Admin | Update request status | Admin logged in, requests exist | 1. Select request from dropdown | Status changes, table updates immediately | High | Done | DEF-AD003
2. Choose new status
3. Click Update
ADMIN-004 | Admin | Statistics calculation | Multiple requests exist | 1. Navigate to Admin panel | Correct counts displayed for each status | Medium | Done | DEF-AD004
2. Check statistics cards
ADMIN-005 | Admin | Verify admin login on CleanCityAdminPanel | Access to the clean city admin panel | 1. Login to the admin panel | Element expected to be interactable | High | Completed | DEF-AD005
2. Click on email input field
3. Type the admin email address
UI-001 | UI/UX | Page navigation | Any page | 1. Click all navigation links | Correct pages load, URL updates | Medium | Done | DEF-U001
2. Check URL and content
UI-002 | UI/UX | Mobile responsiveness | Mobile viewport | 1. Resize to 375x667 | Layout adjusts properly, no horizontal scroll | Medium | Done | DEF-U002
2. Check all pages
UI-003 | UI/UX | Tablet responsiveness | Tablet viewport | 1. Resize to 768x1024 | Layout adjusts properly for tablet | Medium | Done | DEF-U003
2. Check all pages
UI-004 | UI/UX | Form consistency | Any form page | 1. Check all form elements | Uniform styling across all forms | Low | Done | DEF-U004
2. Verify styling
UI-005 | UI/UX | Hamburger menu | Mobile view | 1. Resize to mobile | Menu expands/collapses correctly | Medium | Done | DEF-U005
2. Click hamburger menu
3. Check navigation
AW-001 | Awareness | Page content load | Any user | 1. Navigate to Awareness page | All content loads correctly | Medium | Done | DEF-AW001
2. Check all sections
AW-002 | Awareness | Image loading | Awareness page | 1. Check all images | All images load without errors | Low | Done | DEF-AW002
2. Verify loading state
AW-003 | Awareness | Grid layout | Awareness page | 1. Check awareness cards layout | Cards display in proper grid format | Low | Done | DEF-AW003
2. Verify responsive behavior
SEC-001 | Security | XSS prevention | Any form | 1. Enter <script>alert('XSS')</script> in text fields | Script treated as text, not executed | Critical | Done | DEF-S001
2. Submit
SEC-002 | Security | Input sanitization | Registration form | 1. Enter SQL commands in inputs | Commands treated as text, not executed | Critical | Done | DEF-S001
2. Submit
PERF-001 | Performance | Page load time | Clean cache | 1. Measure main page load time | Pages load within 3 seconds | Medium | Done | DEF-P001
2. Check resource loading
PERF-002 | Performance | Large dataset handling | 50+ requests | 1. Create many requests | App remains responsive | Medium | Done | DEF-P002
2. Check dashboard performance

## DEFECTS_LOG
Defect ID | Title | Module | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Assigned To
DEF-001 | XSS Security Vulnerability | Security | Script tags execute when entered in form inputs | 1. Enter <script>alert('XSS')</script> in any text field | Script should be sanitized and not execute | Script executes in browser | Critical | High | Open | ChifuOnSteroids
2. Submit form
DEF-002 | Data Loss on Browser Clear | Data | All application data lost when browser storage cleared | 1. Create multiple pickup requests | Data should persist or have backup | All user data and requests lost | High | High | Open | ChifuOnSteroids
2. Clear browser storage/data
3. Reload application
DEF-003 | No Form Validation Feedback | Forms | Forms submit without validation error messages | 1. Submit any form with required fields empty | Clear validation messages should appear | No feedback, form may submit | Medium | Medium | Open | ChifuOnSteroids
2. Observe behavior
DEF-004 | Mobile Menu Not Functional | UI | Hamburger menu doesn't respond on mobile view | 1. Resize browser to mobile size | Menu should expand/collapse | No response from menu click | Medium | Medium | Open | ChifuOnSteroids
2. Click hamburger menu
3. Observe behavior
DEF-005 | Filter Count Not Updating | Dashboard | Filter count text doesn't update when filters applied | 1. Apply status or location filters | Text should update with result count | Static text doesn't change | Low | Low | Open | ChifuOnSteroids
2. Check filter count display
DEF-006 | Admin Panel Direct URL Access | Admin Panel | Admin panel accessible without authentication via direct URL | 1. Open browser in incognito | Redirect to login page | Full admin panel loads and is usable | Critical | High | Open | ChifuOnSteroids
2. Navigate to /admin
3. Observe page
DEF-007 | Self-Approval Bypass | Request Table | Resident can approve their own pickup request | 1. Login as resident | Approval requires admin role | Request approved instantly by resident | Critical | High | Open | ChifuOnSteroids
2. Create new pickup request
3. Click Approve on own request
DEF-008 | Cross-User Request Deletion | Request Table | Resident can delete pickup requests of other users | 1. Login as User A | Delete option disabled for non-owned requests | Request deleted successfully | Critical | High | Open | ChifuOnSteroids
2. View all requests
3. Delete request created by User B
DEF-009 | LocalStorage Role Tampering | Authentication | Any user can become admin by editing localStorage | 1. Login as regular user | Server rejects unauthorized action | Full admin access granted | Critical | High | Open | ChifuOnSteroids
2. Open DevTools → localStorage → set role: "admin"
3. Refresh and access admin features
DEF-010 | Session Persists After Logout | Authentication | Logout does not terminate session; back button restores access | 1. Login successfully | Redirected to login screen | User remains fully logged in | Major | High | Open | ChifuOnSteroids
2. Click Logout
3. Press browser back button
DEF-011 | No Password Policy Enforcement | Registration | Registration accepts weak passwords like "1" | 1. Go to registration form | Server rejects weak password | Account created and user logged in | Major | High | Open | ChifuOnSteroids
2. Enter password "1"
3. Submit
DEF-012 | Location Filter Mismatch | Request Table | Selecting "Eldoret" shows Nairobi requests | 1. Go to request table | Only Eldoret requests displayed | Nairobi and other location requests appear | Major | High | Open | ChifuOnSteroids
2. Filter by Location: Eldoret
DEF-013 | Bulk Update Ignores Selection After Sort | Admin Panel | Bulk update applies to all visible rows after sorting | 1. Sort table by date | Only selected rows updated | All rows on current page updated | Critical | High | Open | ChifuOnSteroids
2. Select 2 specific rows
3. Click Bulk Update
DEF-014 | Invalid Email Accepted | Registration | Email validation allows "a@b", "test@" | 1. Enter email as "test@" | Validation error: Invalid email | Form submits successfully | Major | High | Open | ChifuOnSteroids
2. Submit registration
DEF-015 | Hamburger Menu Missing ARIA | Mobile Navigation | Hamburger menu lacks accessibility attributes | 1. Open site on mobile | aria-expanded, aria-controls, aria-label present | No ARIA attributes | Major | High | Open | ChifuOnSteroids
2. Inspect hamburger button
DEF-016 | Blog Post Without Login | Blog Module | Anyone can create blog posts without authentication | 1. Open browser in incognito | Redirect to login or block submission | Blog post created and published anonymously | Critical | High | Open | ChifuOnSteroids
2. Navigate to /blog/create
3. Fill title and content
4. Click Publish
DEF-017 | Blog Admin Panel No Auth | Blog Module | Blog admin panel accessible without login via /admin/blog | 1. Open incognito | Redirect to login page | Full blog admin controls visible and functional | Critical | High | Open | ChifuOnSteroids
2. Go directly to /admin/blog
3. View dashboard
DEF-018 | Dashboard Real-Time Failure | Dashboard | Dashboard counters do not update across browser tabs | 1. Open Dashboard in Tab A | Pending count decreases instantly (e.g. 49 → 48) | Count remains stale until manual refresh | Major | High | Open | ChifuOnSteroids
2. In Tab B, mark request as Completed
3. Switch back to Tab A
DEF-019 | API Rate Limiting Missing | Backend/API | No rate limiting on critical endpoints (login, status update) | 1. Use script to send 1000+ POST requests to /api/update-status | Requests throttled after limit (e.g. 429 Too Many Requests) | All requests succeed without throttling | Critical | High | Open | ChifuOnSteroids
2. Monitor response
DEF-020 | CSRF Protection Absent | Security | No CSRF tokens on state-changing requests | 1. Login to app | Request rejected due to missing CSRF token | Request executes and updates status | Critical | High | Open | ChifuOnSteroids
2. Craft malicious form on external site posting to /api/update-status
3. Submit from external site while logged in
DEF-021 | Password Stored in Plain Text | Database | User passwords stored in plain text in database | 1. Login with password "secret123" | Password should be hashed (bcrypt) | Password visible in DB as "secret123" | Critical | High | Open | ChifuOnSteroids
2. Check users table in database
DEF-022 | No Input Sanitization on Search | Search | SQL injection possible via search field | 1. Enter ' OR 1=1 -- in search box | Search should be sanitized or use prepared statements | All records returned (SQL injection success) | Critical | High | Open | ChifuOnSteroids
2. Submit search
DEF-023 | File Upload No Validation | Upload | Any file type can be uploaded including .exe | 1. Upload test.exe file | File type validation rejects non-allowed files | File uploads and executes | Critical | High | Open | ChifuOnSteroids
2. Check server directory
DEF-024 | No CAPTCHA on Registration | Registration | Automated bot registration possible | 1. Use script to register 100 accounts | Rate limit or CAPTCHA blocks bots | 100 accounts created in 30 seconds | Critical | High | Open | ChifuOnSteroids
2. Monitor registration endpoint
DEF-025 | Admin Logs Missing | Admin Panel | No audit trail of admin actions | 1. Admin approves 5 requests | Logs show who, what, when | No log entries created | Major | High | Open | ChifuOnSteroids
2. Check audit log table
DEF-026 | Email Confirmation Bypassed | Registration | Users can log in without verifying email | 1. Register with unowned email | Account activation requires email click | Login successful without verification | Major | High | Open | ChifuOnSteroids
2. Do not click confirmation link
3. Attempt login
DEF-027 | Export CSV Includes Sensitive Data | Reports | CSV export contains phone numbers and addresses | 1. Click Export All Requests | Only non-sensitive fields exported | Full PII exported to CSV | Major | High | Open | ChifuOnSteroids
2. Download file
DEF-028 | No Session Timeout | Authentication | User session never expires | 1. Login and leave browser open for 24 hours | Session expires after 30 mins inactivity | User still logged in after 24 hours | Major | High | Open | ChifuOnSteroids
2. Return after 24 hours
DEF-029 | Pagination Broken on Large Data | Request Table | Pagination shows incorrect page count | 1. Go to requests with 500+ entries | Page count = 50 pages (10 per page) | Page count shows 1 or wrong number | Major | High | Open | ChifuOnSteroids
2. Click page 2
DEF-030 | Search Returns Deleted Records | Search | Soft-deleted requests appear in search | 1. Delete a request | Deleted records excluded from search | Deleted request appears in results | Major | High | Open | ChifuOnSteroids
2. Search by request ID
DEF-031 | No Rate Limit on SMS API | SMS | Unlimited SMS triggers via API | 1. Send 1000 SMS via /api/send-sms | SMS throttled after 100/day | 1000 SMS sent successfully | Critical | High | Open | ChifuOnSteroids
2. Monitor SMS gateway
DEF-032 | Broken Image Links in Blog | Blog Module | Blog images return 404 | 1. View published blog post | All images load correctly | Multiple images show broken icon | Major | Medium | Open | ChifuOnSteroids
2. Scroll to image section
DEF-033 | Keyboard Trap in Modal | UI | Users cannot exit modal using keyboard | 1. Open any modal (e.g. request details) | Tab/Esc closes modal | Focus trapped inside modal | Major | High | Open | ChifuOnSteroids
2. Press Tab repeatedly
DEF-034 | No Alt Text on Icons | Icons | All icons lack alt attributes | 1. Run accessibility scan | All icons have descriptive alt text | No alt text on 40+ icons | Major | Medium | Open | ChifuOnSteroids
2. View source of dashboard icons
DEF-035 | Filter Reset Clears Form | Data Entry | Reset button clears unsaved form data without warning | 1. Fill pickup form halfway | Confirmation: "Discard changes?" | Form clears silently, data lost | Major | High | Open | ChifuOnSteroids
2. Click Reset
DEF-036 | Login Brute Force Possible | Authentication | No lockout after failed login attempts | 1. Enter wrong password 50 times | Account locked after 5 failed attempts | No lockout – unlimited attempts | Critical | High | Open | ChifuOnSteroids
2. Observe login behavior
DEF-037 | Remember Me Stores Token in localStorage | Authentication | Remember Me saves JWT in localStorage (not HttpOnly cookie) | 1. Login with "Remember Me" checked | JWT stored in secure HttpOnly cookie | JWT visible in localStorage | Critical | High | Open | ChifuOnSteroids
2. Open DevTools → localStorage
DEF-038 | Profile Photo Upload No Resize | Upload | Users can upload 50MB image files | 1. Upload 50MB profile photo | Resize to <2MB or reject large files | File uploads fully, crashes browser | Major | High | Open | ChifuOnSteroids
2. Check upload progress
DEF-039 | Admin Can Delete Own Account | Admin Panel | Admin can delete their own active account | 1. Login as admin | Delete button disabled for self | Account deleted → system locked | Critical | High | Open | ChifuOnSteroids
2. Go to user list → delete self
DEF-040 | No Input Length Limit on Notes | Forms | Notes field accepts unlimited characters | 1. Paste 10,000+ characters into notes | Truncate or warn at 1000 chars | Database error or UI freeze | Major | High | Open | ChifuOnSteroids
2. Submit form
DEF-041 | Timezone Mismatch in Logs | Logging | Timestamp in logs uses server time, not user timezone | 1. User in EAT completes request at 3 PM | Log shows 3:00 PM EAT | Log shows UTC time (12:00 PM) | Major | Medium | Open | ChifuOnSteroids
2. Check activity log
DEF-042 | Mobile View Overlap on Tables | Request Table | Table columns overlap on small screens | 1. Open request table on phone | Horizontal scroll or responsive layout | Columns overlap, unreadable | Major | High | Open | ChifuOnSteroids
2. Scroll horizontally
DEF-043 | Export PDF Missing Footer | Reports | PDF export has no page number or date | 1. Export request report to PDF | PDF includes footer: "Page 1 of 3 ¦ Exported on [date]" | No footer, blank space | Major | Medium | Open | ChifuOnSteroids
2. Open downloaded PDF
DEF-044 | Role Change Not Reflected Until Relogin | Authentication | User role update requires relogin to take effect | 1. Admin changes user from Resident → Driver | Changes apply immediately on next request | User still sees old role until relogin | Major | High | Open | ChifuOnSteroids
2. User refreshes dashboard without relogin
DEF-045 | No Backup of Uploaded Files | Storage | Uploaded files not backed up or versioned | 1. Upload driver license photo | Files stored in redundant storage or versioned | Single copy – risk of data loss | Critical | High | Open | ChifuOnSteroids
2. Simulate server failure
DEF-046 | SQL Injection in Location Filter | Database | Location filter vulnerable to SQL injection | 1. Enter ' OR 1=1 -- in location dropdown | Filter sanitized, shows error | All locations returned | Critical | High | Open | ChifuOnSteroids
2. Submit filter
DEF-047 | No HTTPS Enforcement | Security | HTTP requests accepted, no HSTS | 1. Access site via http://domain.com | Automatic redirect to HTTPS | HTTP loads successfully | Critical | High | Open | ChifuOnSteroids
2. Check browser address bar
DEF-048 | Duplicate Request IDs Possible | Request Management | Same request ID generated for different requests | 1. Create 2 requests within 1 second | Unique sequential IDs generated | Duplicate ID assigned | Critical | High | Open | ChifuOnSteroids
2. Check request table
DEF-049 | No Phone Number Validation | Registration | Invalid phone numbers accepted (e.g. "abc") | 1. Enter phone as "abc123" | KE format validation (+254xxxxxxxxx) | Phone saved as "abc123" | Major | High | Open | ChifuOnSteroids
2. Complete registration
DEF-050 | Cache Poisoning Possible | Performance | Static assets cached indefinitely | 1. Deploy updated CSS file | Versioned cache busting (style.v2.css) | Old CSS served from CDN cache | Major | High | Open | ChifuOnSteroids
2. Hard refresh browser
DEF-051 | No Error Logging on API Failure | Backend | 500 errors not logged with stack trace | 1. Trigger API error (invalid request) | Error logged with full stack trace | Generic "Internal error" only | Major | High | Open | ChifuOnSteroids
2. Check server logs
DEF-052 | Password Reset No Rate Limit | Authentication | Unlimited password reset requests possible | 1. Request password reset 100 times | Throttled after 3 attempts/hour | 100 emails sent instantly | Critical | High | Open | ChifuOnSteroids
2. Check email inbox
DEF-053 | No Content Security Policy | Security | No CSP header – XSS via inline scripts possible | 1. Check response headers | CSP header present (script-src 'self') | No CSP header in response | Critical | High | Open | ChifuOnSteroids
2. Run security scan
DEF-054 | Inactive Users Can Login | Authentication | Disabled accounts still accessible | 1. Admin disables user account | Login blocked with "Account disabled" | Login successful | Major | High | Open | ChifuOnSteroids
2. Disabled user attempts login
DEF-055 | No Database Index on Request Status | Request Table | Slow queries on status filtering (500ms+) | 1. Filter requests by "Pending" | <100ms query response | Slow query detected in logs | Major | High | Open | ChifuOnSteroids
2. Check database query time
DEF-056 | Reset Password' Feature | Authentication | Incase a user forgets their password, they have no option to reset it | 1. Log in using your email address.
|  |  |  | 2. Incase password if forgotten, check for reset password option | Should be able to reset password. | There's no reset password link | Major | High | Completed | Rehema
DEF-057 | Scheduling waste pickups with past dates | Waste Management | A user is able to schedule waste pickups with past dates | 1. On the home page, fill out your information | Past dates should be grey out or users get an error when they put a past date. | Waste pickups can be scheduled with past dates | Major | High | Completed | Rehema
2. On the schedule waste pickup date, put a past date. This will go through
DEF-058 | Inability to edit profile | Dashboard | No option to edit your profile incase you want to change email or username | 1. Navigate to the dashboard | Should be able to edit profile | No option to edit profile | High | High | Completed | Rehema
2. Try edit profile.
DEF-059 | Email input field not interactable during login automation | Admin Panel | During automated login testing using Katalon Recorder, the email field is not interactable | 1.Navigate to the admin panel | Email input should accept typing immediately | Katalon report: Element Is not currently interactable and may not be manipulated | Medium | High | Completed | Rehema
2. Click on email input.
3. Type admin@cleancity.com

## RISK_ANALYSIS
RiskID | RiskCategory | RiskDescription | Impact | Probability | Severity | MitigationStrategy | Owner | Status
RISK-001 | Security | No input sanitization - XSS vulnerability | High | High | Critical | Implement input validation and sanitization library | ChifuOnsteroids | Closed
RISK-002 | Data | LocalStorage data loss on browser clear | High | Medium | High | Implement data export feature and backup prompts | ChifuOnsteroids | Closed
RISK-003 | Security | Hardcoded demo credentials in production | High | Medium | High | Remove hardcoded accounts, implement proper auth system | ChifuOnsteroids | Closed
RISK-004 | Security | No password encryption in storage | High | High | Critical | Implement proper password hashing (bcrypt) | ChifuOnsteroids | Closed
RISK-005 | Performance | LocalStorage size limitations (5MB) | Medium | Medium | Medium | Implement data pagination and archiving system | ChifuOnsteroids | Closed
RISK-006 | Usability | No form validation feedback to users | Medium | High | Medium | Enhance real-time validation with clearer error messages | ChifuOnsteroids | Closed
RISK-007 | Usability | No loading states for form submissions | Low | High | Low | Add loading spinners and disable buttons during submission | ChifuOnsteroids | Closed
RISK-008 | Compatibility | Limited browser compatibility testing | Medium | Medium | Medium | Expand testing to include Safari, Firefox, Edge | ChifuOnsteroids | Closed
RISK-009 | Accessibility | WCAG compliance not verified | Medium | High | Medium | Conduct accessibility audit and implement fixes | ChifuOnsteroids | Closed
RISK-010 | Data | No data persistence across devices | Medium | High | Medium | Plan for cloud synchronization feature | ChifuOnsteroids | Closed
RISK-011 | Performance | Large dataset slows down dashboard | Medium | High | Medium | Implement virtual scrolling or pagination for large tables | ChifuOnsteroids | Closed
RISK-012 | DataIntegrity | Data corruption in LocalStorage | High | Low | High | Add data validation checks and corruption recovery | ChifuOnsteroids | Closed
RISK-013 | Security | CSRF vulnerabilities in form submissions | Medium | Medium | Medium | Implement CSRF tokens for all form submissions | ChifuOnsteroids | Closed
RISK-014 | Compatibility | CSS/JS feature support in older browsers | Medium | Medium | Medium | Use progressive enhancement and feature detection | ChifuOnsteroids | Closed
RISK-015 | Security | Role spoofing via LocalStorage manipulation | High | High | Critical | Enforce server-side RBAC + JWT validation | ChifuOnsteroids | Closed
RISK-016 | Security | XSS via unsanitized community post content | High | High | Critical | Sanitize all user-generated content with DOMPurify | ChifuOnsteroids | Closed
RISK-017 | Security | JS injection in comment input field | High | High | Critical | Block <script>, onerror, onload via CSP + sanitization | ChifuOnsteroids | Closed
RISK-018 | Security | .env file committed to Git with secrets | High | High | Critical | Rotate all keys + remove .env from repo history | ChifuOnsteroids | Closed
RISK-019 | Data | Full user object stored in plaintext LocalStorage | High | High | Critical | Store only JWT token + encrypt sensitive fields | ChifuOnsteroids | Closed
RISK-020 | Security | Unsafe HTML saved and rendered in blog editor | High | High | Critical | Sanitize on input & output using allowlist renderer | ChifuOnsteroids | Closed
RISK-021 | Data | Sample data overwrites production data | High | High | Critical | Disable initializeSampleData() in production build | ChifuOnsteroids | Closed
RISK-022 | Security | No server-side RBAC — client updates persist | High | High | Critical | Validate all mutations on backend with user role | ChifuOnsteroids | Closed
RISK-023 | Security | Admin panel accessible via direct URL | High | High | Critical | Add auth middleware to all /admin/* routes | ChifuOnsteroids | Closed
RISK-024 | Security | Unprotected admin routes allow access | High | High | Critical | Implement route guards + session validation | ChifuOnsteroids | Closed
RISK-025 | Security | No server-side input sanitization | High | High | Critical | Sanitize + validate all API inputs on backend | ChifuOnsteroids | Closed
RISK-026 | Data | Sensitive data exposed in unencrypted LocalStorage | High | High | Critical | Encrypt LocalStorage using CryptoJS / WebCrypto | ChifuOnsteroids | Closed
RISK-027 | Data | clearAllData() wipes data without confirmation | High | High | Critical | Add confirmation modal + audit log | ChifuOnsteroids | Closed
RISK-028 | Security | Client-side login bypasses server validation | High | High | Critical | Require server-authenticated login only | ChifuOnsteroids | Closed
RISK-029 | Security | Plaintext passwords stored in LocalStorage | High | High | Critical | Never store passwords — hash on registration | ChifuOnsteroids | Closed
RISK-030 | Security | No login required to post or comment | High | High | Critical | Require authenticated session for write actions | ChifuOnsteroids | Closed
RISK-031 | Security | API keys exposed in Git commit history | High | High | Critical | Purge repo history + rotate keys | ChifuOnsteroids | Closed
RISK-032 | Testing | Zero unit test coverage | High | High | Critical | Achieve >80% coverage with Jest + RTL | ChifuOnsteroids | Closed
RISK-033 | Security | No comment moderation — spam accepted | High | High | Critical | Add moderation queue or CAPTCHA | ChifuOnsteroids | Closed
RISK-034 | Security | Admin panel publicly accessible at /admin | High | High | Critical | Redirect unauthenticated users to login | ChifuOnsteroids | Closed
RISK-035 | Security | Unsafe HTML execution in rich text editor | High | High | Critical | Use safe HTML renderer + DOMPurify | ChifuOnsteroids | Closed
RISK-036 | Security | XSS risk in comment input field | High | High | Critical | Escape + strip dangerous attributes | ChifuOnsteroids | Closed
RISK-037 | Security | Invalid email formats accepted | High | High | High | Use regex/email validator library | ChifuOnsteroids | Closed
RISK-038 | Security | Weak passwords accepted | High | High | High | Enforce min 8 chars, uppercase, lowercase, number, symbol | ChifuOnsteroids | Closed
RISK-039 | Usability | Past dates allowed in pickup scheduling | High | High | High | Disable past dates in date picker | ChifuOnsteroids | Closed
RISK-040 | Data | No RequestID format validation | High | High | High | Enforce REQ-XXXX regex pattern | ChifuOnsteroids | Closed
RISK-041 | Accessibility | Focus indicators removed (outline:none) | High | High | High | Restore focus styles or use custom visible ring | ChifuOnsteroids | Closed
RISK-042 | Data | Locationfiltershowsincorrectrequests | High | High | High | Fixfilterlogictomatchexactlocation | ChifuOnsteroids | Closed
RISK-043 | Data | Dashboardcountersstaleacrosstabs | High | High | High | UseBroadcastChannelorlocalStorageeventsforsync | ChifuOnsteroids | Closed
RISK-044 | Security | Sessionpersistsafterlogout(Backbutton) | High | High | High | Clearcache+useCache-Control:no-store | ChifuOnsteroids | Closed
RISK-045 | Data | RequestIDcollision—REQ001reused | High | High | High | UseUUIDoratomiccounterforIDs | Victor Mutinda | Closed
RISK-046 | Data | Noconcurrencylock—overwrites | High | High | High | Implementoptimisticlockingorreal-timesync | Victor Mutinda | Closed
RISK-047 | Usability | InvalidblogIDcrashesentireapp | High | High | High | Add404handler+inputvalidation | Victor Mutinda | Closed
RISK-048 | Data | Nocross-tabdatasync | High | High | High | ImplementlocalStorageeventlisteners | Victor Mutinda | Closed
RISK-049 | Data | Harddeletewithnoauditlog | High | High | High | Addsoftdelete+audittrail | Victor Mutinda | Closed
RISK-050 | Data | Democontentvisibleinproduction | High | High | High | Stripdemodatainproductionbuild | Victor Mutinda | Closed
RISK-051 | Performance | 100+commentscrashpage | High | High | High | Implementpaginationorvirtualization | Victor Mutinda | Closed
RISK-052 | Security | Nopasswordstrengthcheckonlogin | High | High | High | Enforcestrengthonregistration | Victor Mutinda | Closed
RISK-053 | Data | Harddeletewithnoundo | High | High | High | Addrecyclebinorundotoast | Victor Mutinda | Closed
RISK-054 | Usability | Formsacceptempty/invalidsubmissions | High | High | High | Addrequired+real-timevalidation | Victor Mutinda | Closed
RISK-055 | Performance | FrequentlocalStoragewritescauselag | High | High | High | Debounceinputs+batchwrites | Victor Mutinda | Closed
RISK-056 | Usability | Nosavefeedbackonactions | High | High | High | Addtoast:"Saved!"onsuccess | Victor Mutinda | Closed
RISK-057 | Data | NoerrorhandlingonJSON.parse | High | High | High | Wrapintry/catch+fallbackdata | Victor Mutinda | Closed
RISK-058 | Accessibility | outline:noneremovesallfocusstyles | High | High | High | Use:focus-visiblewithcustomstyle | Victor Mutinda | Closed
RISK-059 | Data | Malformed/corruptinputsaved | High | High | High | Validateschemabeforesaving | Victor Mutinda | Closed
RISK-060 | Accessibility | Animationsignoreprefers-reduced-motion | Medium | High | Medium | RespectOSsettingwith@media(prefers-reduced-motion) | Victor Mutinda | Closed
RISK-061 | Accessibility | HamburgermenumissingARIAcontrols | Medium | High | Medium | Addaria-expanded+aria-controlstotoggle | Victor Mutinda | Closed
RISK-062 | Accessibility | Noaria-invalidonfailedvalidation | Medium | High | Medium | Setaria-invalid="true"+aria-errormessage | Victor Mutinda | Closed
RISK-063 | Usability | Videoautoplayblockedonmobile | Medium | High | Medium | Addmuted+playsinline+preload="metadata" | Victor Mutinda | Closed
RISK-064 | Data | JSON.parse()crashesoncorruptlocalStorage | Medium | High | Medium | Wrapintry/catch+fallbacktoemptystate | Victor Mutinda | Closed
RISK-065 | Accessibility | Modalhasnofocustrap | Medium | High | Medium | Implementfocustrapwithfirst/lastfocusable | Victor Mutinda | Closed
RISK-066 | Documentation | READMEoutdatedwithlocalhostURLs | Medium | High | Medium | UpdatetoproductionURLs+deployinstructions | Victor Mutinda | Closed
RISK-067 | Mobile | 100vhbreaksmobilelayout | Medium | High | Medium | UsedvhorJSfallbackfordynamicviewport | Victor Mutinda | Closed
RISK-068 | Accessibility | Buttonhoverstateiscolor-only(WCAGfail) | Medium | High | Medium | Addunderlineoriconchangeonhover | Victor Mutinda | Closed
RISK-069 | Accessibility | Textareamissingaria-label | Medium | High | Medium | Addaria-labelorassociatewith<label> | Victor Mutinda | Closed
RISK-070 | Accessibility | Activetabindicatedbycoloronly | Medium | High | Medium | Addaria-selected+visualnon-colorcue | Victor Mutinda | Closed
RISK-071 | Accessibility | Horizontalscrollnotkeyboardaccessible | Medium | High | Medium | Enablearrowkeynavigationinscrollcontainer | Victor Mutinda | Closed
RISK-072 | Security | AvatarURLenumerationrisk | Medium | High | Medium | AddauthcheckorobfuscateIDs | Victor Mutinda | Closed
RISK-073 | Usability | Logouthasnoconfirmationmodal | Medium | High | Medium | Add"Areyousure?"dialog | Victor Mutinda | Closed
RISK-074 | Data | NoerrorhandlingonlocalStorageparse | Medium | High | Medium | Try/catch+schemavalidation | Victor Mutinda | Closed
RISK-075 | Data | Noconcurrencycontrolonedit | Medium | High | Medium | Show"Someoneisediting"warning | Victor Mutinda | Closed
RISK-076 | Data | CommentIDcollisionwithDate.now() | Medium | High | Medium | UseUUIDornanoidforcommentIDs | Victor Mutinda | Closed
RISK-077 | Accessibility | MissingARIAlabelsonicons/buttons | Medium | High | Medium | Addaria-labelorvisuallyhiddentext | Victor Mutinda | Closed
RISK-078 | Data | Deletingpostdeletesallcomments | Medium | High | Medium | Addwarning:"ThiswilldeleteXcomments" | Victor Mutinda | Closed
RISK-079 | Mobile | 100vhcutsoffmobilecontent | Medium | High | Medium | UseCSSenv()orJSheightcalculation | Victor Mutinda | Closed
RISK-080 | Accessibility | Motionsicknessfromanimation | Medium | High | Medium | Reducemotionifprefers-reduced-motion | Rehema Shammah | Closed
RISK-081 | Accessibility | ButtonsongradientfailWCAGcontrast | Medium | High | Medium | Increasecontrastoraddborder/shadow | Rehema Shammah | Closed
RISK-082 | Accessibility | .like/.commentbtnhasnofocusstyle | Medium | High | Medium | Addvisible:focusring | Rehema Shammah | Closed
RISK-083 | Accessibility | .likedstatehaslowcontrast | Medium | High | Medium | Usedarkershadeoriconchange | Rehema Shammah | Closed
RISK-084 | Performance | Novirtualizationincommentssection | Medium | High | Medium | ImplementReactWindoworvirtuallist | Rehema Shammah | Closed
RISK-085 | Usability | Layoutoverflowonsmallscreens | Medium | High | Medium | Addhorizontalscrollorresponsivegrid | Rehema Shammah | Closed
RISK-086 | Accessibility | .community-feedmissingARIAregion | Medium | High | Medium | Addrole="region"+aria-labelledby | Rehema Shammah | Closed
RISK-087 | Usability | .post-cardtextoverflowclipped | Medium | High | Medium | Usetext-overflow:ellipsisorclamp | Rehema Shammah | Closed
RISK-088 | Usability | Inputsacceptjunkdata | Medium | High | Medium | Validateonblur+real-timefeedback | Rehema Shammah | Closed
RISK-089 | Accessibility | Inputfocushasweakstyle | Medium | High | Medium | Usestrongoutlineorglow | Rehema Shammah | Closed
RISK-090 | Accessibility | Buttonsusehovercoloronly | Medium | High | Medium | Addunderlineorscaleonhover | Rehema Shammah | Closed
RISK-091 | Accessibility | Tabsactivestatecolor-only | Medium | High | Medium | Addbottomborderoricon | Rehema Shammah | Closed
RISK-092 | Accessibility | Badgehoverhaslowcontrastchange | Medium | High | Medium | Increasedeltaoraddicon | Rehema Shammah | Closed
RISK-093 | Usability | Fontsizesarefixed | Medium | High | Medium | Userem+allowbrowserzoom | Rehema Shammah | Closed
RISK-094 | Responsiveness | Onlyonebreakpoint | Medium | High | Medium | Addmobile,tablet,desktopbreakpoints | Rehema Shammah | Closed
RISK-095 | Usability | Badgeanimationcauseslayoutshift | Medium | High | Medium | Reservespaceorusetransform | Rehema Shammah | Closed
RISK-096 | Usability | Buttonhoverchangeisinstant | Medium | High | Medium | Addtransition:all0.2sease | Rehema Shammah | Closed
RISK-097 | Usability | Paddingfixed→overflowonsmallscreens | Medium | High | Medium | Use%ormin-padding | Rehema Shammah | Closed
RISK-098 | Design | Colorsarehardcoded | Medium | High | Medium | UseCSSvariablesfortheming | Rehema Shammah | Closed
RISK-099 | Usability | Forminputsshowborder-onlyerrorstate | Medium | High | Medium | Addredoutline+icon+aria-invalid | Rehema Shammah | Closed
RISK-100 | Usability | Avatarfixedsizeonlargescreens | Medium | High | Medium | Usemax-width+object-fit | Rehema Shammah | Closed
RISK-101 | Accessibility | Tabbuttonshavenofocusindicator | Medium | High | Medium | Add:focus-visiblestyle | Rehema Shammah | Closed
RISK-102 | Accessibility | Tablebuttonscolor-onlyhover | Medium | High | Medium | Addunderlineorbackgroundshift | Rehema Shammah | Closed
RISK-103 | Mobile | Tablescrollhardonmobile | Medium | High | Medium | Stackcolumnsoraddswipehint | Rehema Shammah | Closed
RISK-104 | Accessibility | Rowcolorshavelowcontrast | Medium | High | Medium | Increasecontrastratioto≥3:1 | Rehema Shammah | Closed
RISK-105 | Usability | Fontsizesfixedonzoom | Medium | High | Medium | Useremunits+respectbrowserzoom | Rehema Shammah | Closed
RISK-106 | Usability | Cardpaddingcausesoverflow | Medium | High | Medium | Usebox-sizing:border-box+responsivepadding | Rehema Shammah | Closed
RISK-107 | Usability | Animationcauseslayoutshift | Medium | High | Medium | UsetransformorFLIPtechnique | Rehema Shammah | Closed
RISK-108 | Accessibility | Tableheadersmissingsemantics | Medium | High | Medium | Add<thscope="col"> | Rehema Shammah | Closed
RISK-109 | Accessibility | Buttonfocusnotvisible | Medium | High | Medium | Addvisiblefocusring | Rehema Shammah | Closed
RISK-110 | Accessibility | Summarystatsusecolor-onlymeaning | Medium | High | Medium | Addicons+aria-label | Rehema Shammah | Closed
RISK-111 | Responsiveness | Mobilehasonlyonebreakpoint | Medium | High | Medium | Addfluidbreakpoints(min-width) | Rehema Shammah | Closed
RISK-112 | Accessibility | Tableoverflowtrapskeyboard | Medium | High | Medium | Allowarrownavigation+focusmanagement | Rehema Shammah | Closed
RISK-113 | Design | ColorshardcodedinJS/CSS | Medium | High | Medium | MigratetoCSSvariables | Rehema Shammah | Closed
RISK-114 | Data | localStoragesync/quotaloss | Medium | High | Medium | Monitorquota+warnat80% | Rehema Shammah | Closed
RISK-115 | Data | State+Storageraceconditions | Medium | High | Medium | Usemutexorversionedupdates | Rehema Shammah | Closed
RISK-116 | Usability | window.confirmblocksUI | Medium | High | Medium | Replacewithcustommodal | Rehema Shammah | Closed
RISK-117 | Usability | Inputvalidationallowsmalformeddata | Medium | High | Medium | Validateformat+length | Rehema Shammah | Closed
RISK-118 | Accessibility | Missinglabels/scopeonformelements | Medium | High | Medium | Add<label>+for/id+scope | Rehema Shammah | Closed
RISK-119 | Data | Statusstringmatchingfails("pending"vs"Pending") | Medium | High | Medium | Normalizecasebeforecompare | Rehema Shammah | Closed
RISK-120 | Responsiveness | Tableoverflowonmobile | Medium | High | Medium | Stackorhorizontalscrollwithindicators | Rehema Shammah | Closed
RISK-121 | Data | Immutabilitybroken—shallowcopymutation | Medium | High | Medium | UsestructuredCloneordeepcopy | Rehema Shammah | Closed
RISK-122 | Accessibility | Focusstatesmissingonbuttons/inputs | Medium | High | Medium | Add:focus-visibleglobally | ChifuOnsteroids | Closed
RISK-123 | Accessibility | Lighttextonlightbackground | Medium | High | Medium | Ensure≥4.5:1contrast | ChifuOnsteroids | Closed
RISK-124 | Mobile | Overflow/non-responsiveunder350px | Medium | High | Medium | Addmin-width:320px+fluidlayout | ChifuOnsteroids | Closed
RISK-125 | Usability | Hover-onlyfeedbackontouchdevices | Medium | High | Medium | Add:activestate+tapfeedback | ChifuOnsteroids | Closed
RISK-126 | Usability | Fontsizesfixedonzoom | Medium | High | Medium | Userem+allowzoom | ChifuOnsteroids | Closed
RISK-127 | Usability | ValidationreliesonCSSonly | Medium | High | Medium | CombinewithJSvalidation | ChifuOnsteroids | Closed
RISK-128 | Performance | Animationlagonlow-enddevices | Medium | High | Medium | Usewill-change+reducedmotion | ChifuOnsteroids | Closed
RISK-129 | Usability | Chartsclip/overflowonsmallscreens | Medium | High | Medium | Makeresponsiveoraddscroll | ChifuOnsteroids | Closed
RISK-130 | Accessibility | Buttonsshowcolor-onlystate(disabled) | Medium | High | Medium | Addiconoropacitychange | ChifuOnsteroids | Closed

## RECOMMENDATIONS
Priority | Recommendation | Impact | Effort | Owner | Status
Critical | Implement input sanitization for security | High | Medium | Dev Team | In Progress
Critical | Add password encryption/hashing | High | High | Dev Team | In Progress
High | Create data backup/export functionality | High | Medium | Dev Team | In Progress
High | Enhance form validation with real-time feedback | High | Low | Dev Team | In Progress
High | Fix mobile navigation menu | Medium | Low | Dev Team | In Progress
Medium | Implement loading states for all actions | Medium | Low | Dev Team | In Progress
Medium | Add proper error handling and messages | Medium | Medium | Dev Team | In Progress
Medium | Conduct cross-browser compatibility testing | Medium | Medium | QA Team | In Progress
Medium | Implement accessibility improvements | Medium | High | Dev Team | In Progress
Low | Enhance dashboard filter functionality | Low | Low | Dev Team | In Progress
Low | Add confirmation dialogs for destructive actions | Low | Low | Dev Team | In Progress